BISHOPSTON PUMPTRACK

Follow-Up Meeting Notes

26th February 2026 @ 2pm

Attendees:

Bishopston Community Centre:

Gareth Govier (Swansea Council)		Cllr. Andrew Stevens (Swansea CC)

Cllr. Lyndon Jones MBE  (Swansea CC)	Cllr. Julie Jones (BCC)

Kenneth Johannes Waggestad-Stoa & Jeremy Donaldson (Curve Studio)

Sally Anne-Gates and representatives of Bishopston Skatepark Project

On-line:

Sian James (Swansea Council)		Richard Dando (Swansea Council)

Jake Gates					Sam Etheridge

Nicola Matthews				Anthony Jones (Clerk to BCC)

Purpose: To provide an update on the preferred site (Copley Common), outline planning and approval requirements, discuss risks, and agree next steps to progress the pump track project.

1. Background & Current Position

- Copley Common remains the preferred and most viable site for the pump track following several site visits and exploration of alternative locations.

- The site benefits from good access and potential integration with wider community and ecological plans.

- The project faces significant planning complexity due to the land being common land, requiring:

  - A full Swansea Council planning application.

  - A subsequent PEDW (Planning and Environment Decisions Wales) approval under Section 38.

- PEDW do not offer pre-planning advice, increasing uncertainty and underlining the need for expert input.

2. Key Requirements & Constraints

Planning and Approvals

- A two-stage approval approach is required:

  - Swansea Council Planning Approval – must be secured before applying to PEDW.

  - PEDW Section 38 Application – may take 12 months+; timelines vary depending on the project and commoner support.

Specialist Inputs Needed

To progress to planning submission, the following professional work is required:

- Planning consultant – to provide strategic planning advice, reduce risk, and guide Section 38 submission.

- Ecological surveys & reporting – essential for biodiversity requirements and ecological impact mitigation.

- SUDs (drainage) assessment.

- Topographical and tree surveys (some previous outputs exist and may be reusable).

Community members noted that some ecological and survey work has previously been completed or offered free of charge and may be reusable to reduce costs.

3. Engagement Requirements

Commoners

- Commoner support is critical.

- The group must maintain strong communication with the commoners, especially via Peter Lanfear, who has extensive experience with similar applications.

- The preferred approach is to share design concepts early and allow commoners to provide input before finalising plans.

Community Consultation

- Extensive consultation has already taken place over the past years.

- Additional consultation may be needed, but focused on site integration, not design.

- Options include:

  - A single community drop-in event.

  - Presenting the plans concurrently with the formal Swansea Council planning consultation.

4. Design Considerations

- The previously developed pump track design (Clark & Kent) remains the basis. Significant changes are not expected.

- Tarmac continues to be the industry standard surface for safety and usability.

- Ecological considerations may require complementary design features such as:

  - Surrounding permeable materials.

  - Biodiversity improvements (e.g., wildflower planting, habitats, bat/bird boxes).

- The pump track is positioned as a component of a wider ecological and community enhancement plan, increasing the project’s appeal to funders and authorities.

5. Timeline Overview

The group reviewed a draft programme extending to 2029; however, several opportunities were identified to compress the timeline, including:

- Accelerating ecological and SUDs work by beginning discussions immediately.

- Use of existing survey data collected by the skate park team.

- Leveraging local expertise to reduce lead times and costs.

A revised timeline will be drafted and circulated.

6. Agreed Next Steps

- Appoint/engage a planning consultant (contact details shared during meeting).

- Initiate conversations with the ecologist to confirm required survey scope and seasonal timings.

- Review and reuse existing survey and background documentation gathered by the Skate Park Project group.

- Develop a refined project timeline, highlighting areas to shorten.

- Prepare a consolidated action plan and circulate to all attendees via email.

- Compile an attendee register and ensure all relevant stakeholders are included in future communications.

- Arrange the next meeting once initial actions are completed and updated timeline is ready.

The meeting ended at 3pm